## 1st Quarter
First Quarterly Progress Report for Education Sector 2021-2022 (July-September 2021)
Sector: Education
Activity Details | [6 empty] | Physical Achievemnet |  | Financial Acheivement
Sl.No | Name of the work | Location | unit | Source of Funding | Start Date | Completion Date | Progress in % | Progress in detail | Apporved budget (Nu in Million | Expenditure (Nu in million) | utilization in % | Remarks
1 | 6 unit classroom - 1 | Buli CS | 1 | PTA
2 | 32 bedded hostel -2 | Buli CS | 2 | PTA
3 | Procurment of Furniture | Buli CS |  | PTA |  |  | 0% |  | 1
| Total | [5 empty] | 0% |  | 1 | 0
4 | Procurment of Furniture | SHSS |  | PTA |  |  | 0% |  | 0.7
| Total | [5 empty] | 0% |  | 0.7 | 0
5 | 6 unit classroom- 1 | YCS | 1 | PTA | 25.05.2020 | 27.01.2022 | 75% | Masonry work of ground floor completed. under process of preparation of roof slab | 3
6 | Procurment of Furniture | YCS |  | PTA |  |  | 0% |  | 1
7 | Utiltiy Van | YCS | 1 | PTA |  |  | 20% |  | 1
8 | School Bus | YCS | 1 | PTA |  |  | 20% |  | 1.5
| Total | [5 empty] | 0% |  | 6.5 | 0
9 | Construction of one Kitchen sum store | ZHSS | 1 | PTA | 9.11.2020 | 9.10.2021 | 44% |  | 2.5
| Total | [7 empty] | 2.5 | 0
10 | Construction of 4-unit Staff quarter | KPS | 1 | ` | 16.11.2020 |  | 17% |  | 4
11 | Construction of Warden/Matron Quarter | KPS | 2 | PTA |  |  | 30% |  | 2
12 | Major renovation | KPS |  | PTA |  |  |  |  | 3.8
13 | Construction of low cost Dining Hall | KPS | 1 | PTA |  |  | 15% |  | 0.66
14 | Uitlity van | KPS | 1 | PTA |  |  |  |  | 1
| Total | [7 empty] | 11.46 | 0
15 | Annual review meeting | Principals | 2 | RGoB |  |  | 40% | Principals coordination meeting for UK done. LK planned by the end of Oct. | 0.4
16 | Conducting Sports Programs | School |  | RGoB |  |  |  |  | 0
17 | Organizing Regional and National programs | School |  | RGoB |  |  | 0% |  | 0
18 | Training for all NFE Instructors | NFE | 1 | RGoB |  |  | 0% | Scheduled for the month of Nov. & Dec. 2021 | 0.2 |  | 0
19 | Training for ECCD facilitators | ECCD centers | 1 | RGoB |  |  | 0% | Scheduled for the month of Nov. & Dec. 2021 | 0.3
20 | Training and Capacity Building of teachers (PD Program) | All schools | 5 days | RGoB |  |  | 0% | Committee formed, topics identified and budget estimation in progress on advice of hon'ble Dasho | 0
| Total |  |  | RGoB |  |  |  |  | 0.9 | 0
21 | Procurement of stationaries & equipments | All schools |  | RGoB |  |  | 0% |  | 0
| Total |  |  | RGoB |  |  | 0% |  | 0 | 0
22 | Procurement of 100 Bunk beds | SCS | 100 | RGoB |  |  | 100% | Pocurement completed. | 0.65
| Total |  |  | RGoB |  |  |  |  | 0.65 | 0
23 | Maintenance of 20 classrooms | YCS |  | RGoB |  |  | 0% |  | 0
24 | Re-electrifcations of all classrooms and school buildings | YCS |  | RGoB |  |  | 0% |  | 0
| Total |  |  | RGoB |  |  | 0% |  | 0 | 0
25 | Procurement of fan for MP Hall | TLSS |  | RGoB |  |  |  | To be clubbed with re-electrification of classroom. Planned to provide AC. | 0.5
26 | Re-electrifications of all classrooms and school buildings | TLSS |  | RGoB |  |  | 5% |  | 0.5
27 | Re-electrifications of all classrooms and school buildings | ZLSS |  | RGoB |  |  | 5% |  | 0.5
28 | Maintenance of 17 units classrooms, library rooms and administraitve buildings | ZLSS |  | RGoB |  |  | 0% |  | 0
29 | Construction of shed for dinning purposes | ZLSS |  | RGoB |  |  | 0% |  | 0
30 | Maintenance of whole classrooms & Buildings | TLSS |  | RGoB |  |  | 0% |  | 0
31 | Re-electrifications of all classrooms and school buildings | TLSS |  | RGoB |  |  | 0% |  | 0
32 | Maintenance of School buildings and re-electrification | GLSS |  | RGoB |  |  | 10% | Estimation and technical sanction completed. To be executed departmentally | 1
| Total | [7 empty] | 2.5 | 0
[9 empty] | 26.21 | 0

## 2nd Quarter
Second Quarterly Progress Report for Education Sector 2021-2022 (Oct- Dec. 2021)
Sector: Education
Activity Details | [6 empty] | Physical Achievemnet |  | Financial Acheivement
Sl.No | Name of the work | Location | unit | Source of Funding | Start Date | Completion Date | Progress in % | Progress in detail | Apporved budget (Nu in Million | Expenditure (Nu in million) | utilization in % | Remarks
1 | 6 unit classroom - 1 | Buli CS | 1 | PTA | 2020-10-06 | 2021-10-05 | 100 | Completed and taken Over | 3 | 8.4m | 100%
2 | 32 bedded hostel -2 | Buli CS | 2 | PTA | Feb-02 | 2022-02-02 | 70 | Finishing works Plastering, Fixing of GRC, Mosic, Marbles and Painting works going on ' | 12 | 10 | 50%
3 | Procurment of Furniture | Buli CS |  | PTA |  |  |  | To be procured in the FY 2021-22 | 1 |  |  | List compiled and submitted to Procurement officer
| Total | [7 empty] | 16
4 | Procurment of Furniture | SHSS |  | PTA |  |  |  | Furniture procured and supplied to school in 2020-21 FY only | 0.7 |  | 100% | May be the Budget adjustement is to be made in the system
| Total | [7 empty] | 0.7
5 | 6 unit classroom- 1 | YCS | 1 | PTA | 25.05.2020 | 27.01.2022 | 75% | Masonry work of ground floor completed and unnder porcess of preparation of roof slab | 3
6 | Procurment of Furniture | YCS |  | PTA |  |  |  | To be procured in the FY 2021-22 | 1 |  |  | List compiled and submitted to Procurement officer
7 | Utiltiy Van | YCS | 1 | PTA |  |  | 20 | To be procured in the FY 2021-22 | 1
8 | School Bus | YCS | 1 | PTA |  |  | 20 | To be procured in the FY 2021-22 | 1.5
| Total | [7 empty] | 6.5
9 | Construction of one Kitchen sum store | ZHSS | 1 | PTA | 9.11.2020 | 9.10.2021 | 65% | Reinforcement for the roof slab completed | 2.5 | 2m
| Total | [7 empty] | 2.5
10 | Construction of 4-unit Staff quarter | KPS | 1 | PTA | 16.11.2020 |  | 52% | Warden qtr at roof level and Matrons qtr at door level and wood work completed. | 4
11 | Construction of Warden/Matron Quarter | KPS | 2 | PTA |  |  |  | Roofing completed | 2
12 | Major renovation | KPS |  | PTA |  |  |  | Completed | 3.8
13 | Construction of low cost Dining Hall | KPS | 1 | PTA |  |  |  | Seeking approval from MoF | 0.66
14 | Uitlity van | KPS | 1 | PTA |  |  |  | To be procured in the FY 2021-22 | 1
| Total | [7 empty] | 11.46
15 | Annual review meeting | Principals | 2 | RGoB |  |  | 100% | Principals coordination meeting for UK done. LK planned by the end of Oct. | 0.4 |  |  | Principals meeting conducted and is completed
18 | Training for all NFE Instructors | NFE | 1 | RGoB |  |  | 0% | Scheduled for the month of Nov. & Dec. 2021 | 0.2 |  | 0 | Being conducted at YCS
19 | Training for ECCD facilitators | ECCD centers | 1 | RGoB |  |  | 0% | Scheduled for the month of Nov. & Dec. 2021 | 0.3 |  |  | Scheduled to be conducted in February
20 | Training and Capacity Building of teachers (PD Program) | All schools | 5 days | RGoB |  |  | 0% | Committee formed, topics identified and budget estimation in progress on advice of hon'ble Dasho | 0 |  |  | I day training for all Dzo. Teachers in UK schools conducted in two clusters
| Total |  |  | RGoB |  |  |  |  | 0.9 | 0
21 | Procurement of stationaries & equipments | All schools |  | RGoB |  |  | 0% |  | 0
| Total |  |  | RGoB |  |  | 0% |  | 0 | 0
22 | Procurement of 100 Bunk beds | SCS | 100 | RGoB |  |  | 100% | Pocurement completed. | 0.65 |  |  | Completed
| Total |  |  | RGoB |  |  |  |  | 0.65 | 0
25 | Procurement of fan for MP Hall | TLSS |  | RGoB |  |  |  |  | 0.5 |  |  | To be clubbed with re-electrification of classroom. Planned to provide AC.
26 | Re-electrifications of all classrooms and school buildings | TLSS |  | RGoB |  |  | 5% |  | 0.5 |  |  | Work Awarded
27 | Re-electrifications of all classrooms and school buildings | ZLSS |  | RGoB |  |  | 5% |  | 0.5 |  |  | Work Awarded
32 | Maintenance of School buildings and re-electrification | GLSS |  | RGoB |  |  | 78% | All work completed except the electrification part | 1 |  |  | As per the Principal
| Total | [7 empty] | 2.5 | 0
Ad-hoc (emergency)
| Maintenance of Boys Hostel | GLSS | [9 empty] | DLTC approved to deploy the shortage EGP method and execute at the earliest possible
| Maintenance of four units classroom block | GLSS
| Re-construction of Dinning Hall | GLSS
Total
| Tama HSS Maintenance |  |  | RGoB | 2021-09-09 | 09.03/2021 | 30% | Footpath laid and done with demolishing work | 30 | 10m | 30%
Total
| Construction of ICT Labs | Buli CS | [5 empty] | 100% |  |  |  | Handing taking done and final bill paid
| Construction of ICT Labs | Pantang PS | [5 empty] | 100% |  |  |  | Handing taking done and final bill paid
| Construction of ICT Labs | Panbang PS | [5 empty] | 100% |  |  |  | Handing taking done and final bill paid
| Construction of ICT Labs | Zhemgang LSS | [5 empty] | 100%
Total
| Construction of ECCD structure | Trashibi pPS | [5 empty] | 100% | 0.5 |  |  | Handing taking done and final bill paid
Total
| Refurbishing of kitchen cum store | YCS | [5 empty] | 98% | 0.699 | 0.5 | 90% | submitted the completion report
Activities to be Proposed During Mid Term Review Meet.
1 | Scouting program
1.1 | Resource development: 1. human resource & 2. Materials
1.1 | Training (Cub masters, scouts conference, awards…) and camps
1.2 | Scarf and badges procurement
1.3 | Tents and mics.
2 | ECCD :
1.1 : Material Development
1.2 : Maintenance budget
1.3 : Refreshers course
NFCED
| Materials Procurement (CLC) | 60000
Refreshers’ course (facilitators)
Refurbishment of old Dining hall for backing/CLC activities
Procurement of tray and other accessory for backing purposes
Youth centre,
Youth camp and other advocacy programs
Professional Development for teachers
Construction work
Maintenance of Teachers Qtr. and school at SCS Nu. 215,000.00 (negotiated amount).
Projectors and equipment procured for schools Nu. 184,349.00
Construction of MPH and renovation work of 32 bedded hostel at Gomphu LSS.
Construction of MPH at Panbang PS (Emergency)

## proposal
List of Activities to be proposed for support during the Midterm Review
Sl.no. | Activities | School | Estimate | Justification
1 | Procurement of AC for 6 unit classroom and MPH at SCS & TLSS | 6 units classroom and MPH at SCS & MPH & classrooms at TLSS |  | Dasho Approved the activity during the familiarization visit and estimates worked out by Procurement. Could not procured due to un availability of Fund. The schools are in extremely hot and humid area
2 | Supply of Projector Accessories | Secondary & larger Primary Schools |  | Notesheet approved and materials supplied. Yet the bill remains pending due to non availability of budget. The supply was initiated to support to help schools for mounting Projectors in classroom ceiling
3 | MPH reconstruction | Panbang PS |  | Gewog initiated maintenance of dinning hall yet during the close examination the structure was found irrepairable and risky to the lives of students
| Gomphu LSS Maintenance/Contruction |  |  | Gomphu school is one of the oldest LSS. The 32 beded boys hosted was damaged by earthquake in 2021. The dinning hall was dismentaled considering the risk that posed t the lives of the students and treachers. The sector through Dasho Dzongda explored support from MoE & GNHC but failed. Owing to the emergency the work is awarded and required budget
4 | Replacement of metalic railing/concrete tagzee for 2 six unit classroom block | Zhemgang LSS |  | Two six unit classrooms a ZLSS wooden railing was observed to be risky and was a Royal Command to replace it by concrete railing in 2014. To this date it stands and has become riskier with age. Felt to install concrete or matellic railing which ever is easier/comvenient
5 | Red carpet at ZCS dinning hall | Zhemgang CS | 90000 | Zhemgang CS do not have furnitures in the dinning hall. The practiced traditional way of dining and serving meals. They sit on the floor and the carpets used in the hall are extremely old and stinking. Felt the need to replace carpets for health and sanitation.
6 | Refurbishing and setting of Old MPH at ZCS for setting up backing room | CLC, Zhemgang |  | Zhemgang Community Learning Centre is provided with Backing oven (heavy duty) by NFCED, MoE Thimphu for skill development. At the moment it is housed in library room and is not hygenic. The sector felt the need t provide them with proper space for backing purposes and also few equipments to add on what they have. The sector plans to supply breads to two schools on weekly basis and help the centre generate some roling fund to meet the running cost.
7 | Additional Equipment …....for CLC
8 | Construction of Canopy | Zhemgang CS | 21475 | ZCS proposal was approved vide notesheet …..... Bill pending due to non availability of fund
9 | Panting of Galary at Assembly Ground | Zhemgang CS | 179602.22 | ZCS proposal was approved vide notesheet …..... Bill pending due to non availability of fund
10 | Cub master training (scouts) |  |  | Whole school scouting program I school throughout the country will be introduced from this academic year. Need to train some teachers to equip them with skills and kowledge of scouting at cluster levels
11 | Material procurement (scouts) |  |  | Will required scarf and badges for the new scouts
12 | Procurement of Bus | YCS | 1.5 | Sector explored additional budget from the MoE/GNHC but failed. Need to procure the vehicle for the schools. AWP
13 | Procurement of Utility Van | YCS & KPS | 2
Note on D8: Microsoft Office User: For dining purposes.

## 3rd Quarter
Third Quarterly Progress Report for Education Sector 2021-2022 (Jan - March 2022)
Sector: Education
Activity Details | [6 empty] | Physical Achievemnet |  | Financial Acheivement
Sl.No | Name of the work | Location | unit | Source of Funding | Start Date | Completion Date | Progress in % | Progress in detail | Apporved budget (Nu in Million | Expenditure (Nu in million) | utilization in % | Remarks
1 | 6 unit classroom - 1 | Buli CS | 1 | PTA | 2020-10-06 | 2021-10-05 | 100 | Completed and taken Over | 3 | 8.4m | 100%
2 | 32 bedded hostel -2 | Buli CS | 2 | PTA | Feb-02 | 2022-02-02 | 70 | Finishing works Plastering, Fixing of GRC, Mosic, Marbles and Painting works going on ' | 12 | 10 | 50%
3 | Procurment of Furniture | Buli CS |  | PTA |  |  |  | To be procured in the FY 2021-22 | 1 |  |  | List compiled and submitted to Procurement officer
| Total | [7 empty] | 16
4 | Procurment of Furniture | SHSS |  | PTA |  |  |  | Furniture procured and supplied to school in 2020-21 FY only | 0.7 |  | 100% | May be the Budget adjustement is to be done in Accounts section.
| Total | [7 empty] | 0.7
5 | 6 unit classroom- 1 | YCS | 1 | PTA | 25.05.2020 | 27.01.2022 | 75% | Masonry work of ground floor completed and unnder porcess of preparation of roof slab | 3
6 | Procurment of Furniture | YCS |  | PTA |  |  |  | To be procured in the FY 2021-22 | 1 |  |  | List compiled and submitted to Procurement officer
7 | Utiltiy Van | YCS | 1 | PTA |  |  | 20 | To be procured in the FY 2021-22 | 1
8 | School Bus | YCS | 1 | PTA |  |  | 20 | To be procured in the FY 2021-22 | 1.5
| Total | [7 empty] | 6.5
9 | Construction of one Kitchen sum store | ZHSS | 1 | PTA | 9.11.2020 | 9.10.2021 | 65% | Reinforcement for the roof slab completed | 2.5 | 2m
| Total | [7 empty] | 2.5
10 | Construction of 4-unit Staff quarter | KPS | 1 | PTA | 16.11.2020 |  | 52% | Warden qtr at roof level and Matrons qtr at door level and wood work completed. | 4
11 | Construction of Warden/Matron Quarter | KPS | 2 | PTA |  |  |  | Roofing completed | 2
12 | Major renovation | KPS |  | PTA |  |  |  | Completed | 3.8
13 | Construction of low cost Dining Hall | KPS | 1 | PTA |  |  |  | Seeking approval from MoF | 0.66
14 | Uitlity van | KPS | 1 | PTA |  |  |  | To be procured in the FY 2021-22 | 1
| Total | [7 empty] | 11.46
15 | Annual review meeting | Principals | 2 | RGoB |  |  | 100% | Principals coordination meeting for UK done. LK planned by the end of Oct. | 0.4 |  |  | Principals meeting conducted and is completed
18 | Training for all NFE Instructors | NFE | 1 | RGoB |  |  | 0% | Scheduled for the month of Nov. & Dec. 2021 | 0.2 |  | 0 | Being conducted at YCS
19 | Training for ECCD facilitators | ECCD centers | 1 | RGoB |  |  | 0% | Scheduled for the month of Nov. & Dec. 2021 | 0.3 |  |  | Scheduled to be conducted in February
20 | Training and Capacity Building of teachers (PD Program) | All schools | 5 days | RGoB |  |  | 0% | Committee formed, topics identified and budget estimation in progress on advice of hon'ble Dasho | 0 |  |  | I day training for all Dzo. Teachers in UK schools conducted in two clusters
| Total |  |  | RGoB |  |  |  |  | 0.9 | 0
21 | Procurement of stationaries & equipments | All schools |  | RGoB |  |  | 0% |  | 0
| Total |  |  | RGoB |  |  | 0% |  | 0 | 0
22 | Procurement of 100 Bunk beds | SCS | 100 | RGoB |  |  | 100% | Pocurement completed. | 0.65 |  |  | Completed
| Total |  |  | RGoB |  |  |  |  | 0.65 | 0
25 | Procurement of fan for MP Hall | TLSS |  | RGoB |  |  |  |  | 0.5 |  |  | To be clubbed with re-electrification of classroom. Planned to provide AC.
26 | Re-electrifications of all classrooms and school buildings | TLSS |  | RGoB |  |  | 5% |  | 0.5 |  |  | Work Awarded
27 | Re-electrifications of all classrooms and school buildings | ZLSS |  | RGoB |  |  | 5% |  | 0.5 |  |  | Work Awarded
32 | Maintenance of School buildings and re-electrification | GLSS |  | RGoB |  |  | 78% | All work completed except the electrification part | 1 |  |  | As per the Principal
| Total | [7 empty] | 2.5 | 0
| Maintenance of Boys Hostel | GLSS | [9 empty] | DLTC approved to deploy the shortage EGP method and execute at the earliest possible
| Maintenance of four units classroom block | GLSS
| Re-construction of Dinning Hall | GLSS
Total
| Tama HSS Maintenance |  |  | RGoB | 2021-09-09 | 09.03/2021 | 30% | Footpath laid and done with demolishing work | 30 | 10m | 30%
Total
| Construction of ICT Labs | Buli CS | [5 empty] | 100% |  |  |  | Handing taking done and final bill paid
| Construction of ICT Labs | Pantang PS | [5 empty] | 100% |  |  |  | Handing taking done and final bill paid
| Construction of ICT Labs | Panbang PS | [5 empty] | 100% |  |  |  | Handing taking done and final bill paid
| Construction of ICT Labs | Zhemgang LSS | [5 empty] | 100%
Total
| Construction of ECCD structure | Trashibi pPS | [5 empty] | 100% | 0.5 |  |  | Handing taking done and final bill paid
Total
| Refurbishing of kitchen cum store | YCS | [5 empty] | 98% | 0.699 | 0.5 | 90% | submitted the completion report

## 4th Quarter)
Fourth Quarterly Progress Report for Education Sector 2021-2022 (April - May 2022)
Sector: Education
Activity Details | [6 empty] | Physical Achievemnet |  | Financial Acheivement
Sl.No | Name of the work | Location | unit | Source of Funding | Start Date | Completion Date | Progress in % | Progress in detail | Apporved budget (Nu in Million | Expenditure (Nu in million) | utilization in % | Remarks
1 | 6 unit classroom - 1 | Buli CS | 1 | PTA |  |  | 100% | Completed | 3.16 | 1.864 | 58.9873
2 | 32 bedded hostel -2 | Buli CS | 2 | PTA |  |  | 100% | Completed | 12 | 11.865 | 98.875
3 | Procurment of Furniture | Buli CS |  | PTA |  |  | 100% | Completed | 1 | 0.997 | 99.7
| Total | [7 empty] | 16.16 | 14.726 | 91.1262
4 | Procurment of Furniture | SHSS |  | PTA |  |  | 100% | Completed | 0.77 | 0.77 | 100
| Total | [7 empty] | 0.77 | 0.77 | 100
5 | 6 unit classroom- 1 | YCS | 1 | PTA |  |  | 95% | ongoing | 5.5 | 4.522 | 82.2182
6 | Procurment of Furniture | YCS |  | PTA |  |  | 100% | Completed | 1 | 1 | 100
8 | School Bus | YCS | 1 | PTA |  |  | 100% | Completed | 2.5 | 2.5 | 100
| Total | [7 empty] | 9 | 8.022 | 89.1333
9 | Construction of one Kitchen sum store | ZHSS | 1 | PTA |  |  | 70% | ongoing | 2.5 | 0.7 | 28
| Total | [7 empty] | 2.5 | 0.7 | 28
15 | Annual review meeting | Principals | 2 | RGoB |  |  | 100% | Meeting conducted sepperatly for UK and LK schools | 0.42 | 0.418 | 99.5238
| Total |  |  | RGoB |  |  |  |  | 0.42 | 0.42 | 100
22 | Procurement of 100 Bunk beds | SCS | 100 | RGoB |  |  | 100% | Pocurement completed. | 0.77 | 0.77 | 100
| Total | [7 empty] | 0.77 | 0.77 | 100
26 | Re-electrifications of all classrooms and school buildings | TLSS |  | RGoB |  |  | 100% | Completed | 1 | 1 | 100
27 | Re-electrifications of all classrooms and school buildings | ZLSS |  | RGoB |  |  | 100% | Completed | 0.5 | 0.5 | 100
32 | Maintenance of School buildings and re-electrification | GLSS |  | RGoB |  |  | 100% | Estimation and technical sanction completed. To be executed departmentally | 1.3 | 1.297 | 99.7692
| Construction of 200 capacity dinning hall & Maintenance of 32 bedded hostel and Administration block | GLSS |  | RGoB |  |  | 57.5% | ongoing | 1.282 | 1.282 | 100
| Total | [7 empty] | 4.082 | 4.079 | 99.9265